THE LEGIT TALKS NAARI LED VYAPAAR Launch Command Centre Campaign Mission Control Manual

Campaign Launch: 23 June 2026 ¦ Phase: Impact Sprint ¦ Internal Document ¦ Version 1.0

Discover. Connect. Rise.

An Initiative by The Legit Talks

Table of Contents

1.  Purpose of this Document

2.  Our Mission

3.  Primary Objective

4.  Success Metrics

5.  Campaign Funnel

6.  Team Structure

7.  Daily Priorities

8.  Content Checklist

9.  Every Content Should Answer

10.  Content Pillars

11.  Daily Backend Checklist

12.  WhatsApp Community Workflow

13.  Founder Introduction Template

14.  Community Golden Rule

15.  Comment Management

16.  Live Session Checklist

17.  Community Health Check

18.  Escalation Matrix

19.  Crisis Response

20.  End of Day Review

21.  Weekly Review

22.  Campaign Mantra

23.  Our Definition of Success

24.  The Final Reminder to the Team

1. Purpose of this Document

This document serves as the central operating manual for the launch and execution of the Naari Led Vyapaar campaign.

Its purpose is to ensure that every team member understands:

- The mission

- The priorities

- Daily responsibilities

- Campaign goals

- Team coordination

- Founder experience

- Success metrics

Every decision during the campaign should align with the vision outlined in this manual.

2. Our Mission

We are not launching a campaign.

We are launching a movement.

Our goal is not simply to gain followers or generate engagement.

Our goal is to ensure that women entrepreneurs feel seen, celebrated, supported, and inspired.

Every post, conversation, story, and interaction should move us closer to that mission.

3. Primary Objective

IMPACT

Create visibility for women-led businesses while establishing The Legit Talks as a trusted platform for authentic stories and meaningful communities.

4. Success Metrics

Primary KPIs

- 50 Founder Applications

- 25 Active Founders

- 500 New Instagram Followers

Secondary KPIs

- Community engagement

- Founder introductions

- Story shares

- Live participation

- Founder referrals

- Collaboration requests

- Positive testimonials

5. Campaign Funnel

Awareness

↓

Interest

↓

Comment on Campaign Post

↓

Application Form Submission

↓

Internal Review

↓

Founder Approval

↓

Welcome Message

↓

WhatsApp Community

↓

Founder Introduction

↓

Community Engagement

↓

Founder Spotlight

↓

Long-Term Community Member

6. Team Structure

| Campaign Lead | - Overall strategy, approvals, decision-making, partnerships, and issue resolution. |
| --- | --- |

| Community Manager | - Founder onboarding. - Community moderation. - Daily engagement. - Founder support. - Retention. |
| --- | --- |

| Social Media Manager | - Campaign publishing. - Content scheduling. - Engagement monitoring. - Comment management. - Story updates. |
| --- | --- |

| Designer | - Campaign creatives. - Templates. - Founder features. - Story assets. - Event graphics. |
| --- | --- |

| Video Editor | - Reels. - Live highlights. - Founder edits. - Recap videos. - Testimonials. |
| --- | --- |

| Host | - Live sessions. - Founder interviews. - Community interactions. - Event moderation. |
| --- | --- |

7. Daily Priorities

Every morning, ask:

Have we responded to every founder?

Have we welcomed new applications?

Have we replied to comments?

Have we encouraged conversations?

Have we celebrated someone today?

Have we shared one inspiring story today?

If the answer is no, that becomes the priority.

8. Content Checklist

Every content piece should include at least one of the following:

- A founder story

- A human emotion

- A relatable struggle

- An inspiring lesson

- A business journey

- A call to action

- A reason to participate

Content should make people feel something before asking them to do something.

9. Every Content Should Answer

Why should I stop scrolling?

Why should I care?

Why should I join?

Why should I trust TLT?

Why should I share this?

If the content does not answer these questions, revise it.

10. Content Pillars

| Founder Stories | Real journeys. Failures. Wins. Lessons. |
| --- | --- |

| Business Spotlights | Introduce women-led ventures. Show the person behind the business. |
| --- | --- |

| Community Moments | Founder introductions. Collaborations. Behind-the-scenes. Testimonials. |
| --- | --- |

| Educational Content | Marketing. Mindset. Business tools. Growth. Confidence. |
| --- | --- |

| Movement Building | Why Naari Led Vyapaar exists. Why stories matter. Why women need communities. The long-term vision. |
| --- | --- |

11. Daily Backend Checklist

| Morning | - Review applications. - Respond to DMs. - Approve founders. - Schedule content. - Brief the team. |
| --- | --- |

| Afternoon | - Monitor engagement. - Welcome new founders. - Follow up with pending applicants. - Share reminders. |
| --- | --- |

| Evening | - Publish key content. - Engage with comments. - Update metrics. - Prepare next day. |
| --- | --- |

12. WhatsApp Community Workflow

When a founder joins:

1.  Send welcome message.

2.  Share Founder Handbook.

3.  Share Founder Charter.

4.  Share introduction format.

5.  Encourage introduction.

6.  Personally welcome the founder.

7.  Tag active founders to greet her.

8.  Encourage conversations.

No founder should feel ignored during her first week.

13. Founder Introduction Template

Every founder introduces herself using:

- Name

- City

- Business Name

- What do you do?

- Why did you start?

- One magical thing that happened after starting

- One difficult experience

- One challenge you’re currently facing

- One way the community can support you

- One way you want to contribute

14. Community Golden Rule

Every founder should receive at least one meaningful reply to her introduction.

No introduction should go unnoticed.

15. Comment Management

Reply to:

- Every founder question

- Every application enquiry

- Every nomination

- Every appreciation comment

People remember conversations more than content.

16. Live Session Checklist

Before

☐  Confirm guest.

☐  Test audio/video.

☐  Share reminder.

☐  Prepare questions.

During

☐  Welcome audience.

☐  Introduce founder.

☐  Encourage comments.

☐  Ask audience questions.

After

☐  Thank guest.

☐  Save recording.

☐  Share highlights.

☐  Follow up.

17. Community Health Check

Track daily:

- New applications

- New founders

- Active conversations

- Introductions posted

- Collaborations started

- Positive testimonials

- Founder questions

- Response time

Healthy communities create returning members.

18. Escalation Matrix

| Level 1 | Community Manager resolves. |
| --- | --- |

| Level 2 | Campaign Lead reviews. |
| --- | --- |

| Level 3 | Leadership decision. |
| --- | --- |

Document every major issue.

19. Crisis Response

Pause.

Verify.

Discuss internally.

Respond respectfully.

Protect trust.

Never respond emotionally.

20. End of Day Review

Every evening ask:

What worked today?

What didn’t?

Who needs follow-up?

Who deserves recognition?

What did founders ask for?

What should tomorrow improve?

Small daily improvements create exceptional campaigns.

21. Weekly Review

Review:

- Applications

- Active founders

- Community growth

- Engagement

- Content performance

- Collaborations

- Testimonials

- Team learnings

Celebrate wins before discussing challenges.

22. Campaign Mantra

We are not chasing virality.

We are building credibility.

We are not building followers.

We are building founders.

We are not creating content.

We are creating confidence.

23. Our Definition of Success

Success is a woman introducing herself for the first time.

Success is a founder receiving her first collaboration.

“Because of this community, I continued building.”

If that happens, the campaign has succeeded.

24. The Final Reminder to the Team

Every reel will be forgotten.

Every post will eventually disappear.

Algorithms will change.

Numbers will fluctuate.

But the way a founder feels after interacting with Naari Led Vyapaar will stay with her for years.

Choose people over performance.

Choose conversations over content.

Choose community over campaigns.

That is how movements are built.

DISCOVER • CONNECT • RISE Internal Mission Statement The Legit Talks ¦ Building stories. Building communities. Building legacies.

An Initiative by The Legit Talks  |  Launch Command Centre — Version 1.0  |  Internal Document