THE LEGIT TALKS NAARI LED VYAPAAR Standard Operating Procedures (SOP) Manual Campaign Operations Handbook

Version 1.0 ¦ Confidential – Internal Use Only

Discover. Connect. Rise.

An Initiative by The Legit Talks

Table of Contents

1.  Purpose of this Manual

2.  Campaign Governance

3.  Team Roles & Accountability

4.  Campaign Timeline

5.  Daily Operating Rhythm

6.  Founder Application SOP

7.  Founder Selection SOP

8.  Founder Communication SOP

9.  WhatsApp Community SOP

10.  Content Production SOP

11.  Live Session SOP

12.  Community Engagement SOP

13.  Paid Ads SOP

14.  Analytics & Reporting SOP

15.  Crisis & Escalation SOP

16.  Campaign Closing SOP

17.  Post-Campaign SOP

18.  Campaign Health Dashboard

19.  The Operational Golden Rule

20.  Final Declaration & Internal Motto

1. Purpose of this Manual

This manual establishes the operational standards for planning, executing, monitoring, and concluding Naari Led Vyapaar.

Its objective is to ensure consistency, professionalism, transparency, and a founder-first experience across every edition of the campaign.

Every team member should be familiar with this manual before the campaign begins.

2. Campaign Governance

Campaign Lead

The Campaign Lead is the final decision-maker for all campaign-related matters.

Responsibilities include:

- Strategic oversight

- Timeline management

- Team coordination

- Final approvals

- Crisis decisions

- KPI review

No major campaign change should be implemented without Campaign Lead approval.

3. Team Roles & Accountability

| Campaign Lead | - Reviews campaign progress daily - Conducts stand-up meetings - Tracks KPIs - Approves founder selection - Signs off on campaign closure |
| --- | --- |

| Community Manager | - Reviews applications - Welcomes founders - Moderates WhatsApp group - Answers founder queries - Maintains founder database |
| --- | --- |

| Social Media Manager | - Publishes approved content - Replies to comments and DMs - Encourages community engagement - Tracks platform interactions - Flags issues requiring escalation |
| --- | --- |

| Designer | - Produces campaign creatives - Maintains visual consistency - Updates templates - Delivers assets on schedule |
| --- | --- |

| Video Editor | - Edits reels and interviews - Creates highlight clips - Delivers founder showcase videos - Maintains brand tone |
| --- | --- |

| Ads Manager | - Launches campaigns - Monitors spend - Optimises performance - Reports daily metrics |
| --- | --- |

4. Campaign Timeline

| Phase A Preparation (7 Days) | Objectives: - Finalise assets - Test systems - Assign responsibilities - Prepare communication templates - Verify application flow Deliverables: ✓ Application Form ✓ Founder Tracker ✓ WhatsApp Business Setup ✓ Content Calendar ✓ Campaign FAQ ✓ Welcome Kit ✓ Internal Dashboard |
| --- | --- |

| Phase B Discovery Campaign (7–10 Days) | Objectives: - Drive awareness - Receive applications - Build trust - Generate participation Deliverables: ✓ Publish content ✓ Monitor applications ✓ Respond to enquiries ✓ Track metrics ✓ Review performance |
| --- | --- |

| Phase C Showcase & Wrap-Up (3 Days) | Objectives: - Celebrate founders - Publish recap - Collect testimonials - Prepare transition to Community Phase |
| --- | --- |

5. Daily Operating Rhythm

| Morning 9:00–10:00 AM | - Previous day's performance - New founder applications - Content status - Community updates - Issues requiring action - Priorities for the day |
| --- | --- |

Maximum meeting duration: 30 minutes.

| Midday Community & Social | - Community Manager: Reviews new submissions, welcomes accepted founders, answers pending messages - Social Media Manager: Responds to engagement, shares founder mentions, tracks conversations |
| --- | --- |

| Evening Campaign Lead Review | - KPIs - Ad performance - Community health - Content delivery - Team updates |
| --- | --- |

Daily progress is documented.

6. Founder Application SOP

Founder discovers campaign.

↓

Clicks application link.

↓

Completes official form.

↓

Submission logged in Founder Tracker.

↓

Community Manager reviews within 24 hours.

↓

Acceptance or pending communication sent.

Application Review Checklist

Confirm:

✓  Founder name

✓  Business name

✓  Business category

✓  Contact details

✓  Story completeness

✓  Social media links

✓  Consent for content usage

Incomplete applications should receive one follow-up request before being marked inactive.

7. Founder Selection SOP

Selection Criteria:

- Story authenticity

- Uniqueness of journey

- Community impact

- Business purpose

- Alignment with campaign values

Selection should never be based solely on follower count or business size.

Final approval rests with the Campaign Lead.

8. Founder Communication SOP

Response Standard

Every founder enquiry should receive an initial response within 24 hours.

Tone

- Warm.

- Respectful.

- Clear.

- Encouraging.

- Professional.

Communication Principles

- Avoid jargon

- Avoid automated-sounding language

- Use founder's name

- Confirm next steps

- End with appreciation

Every message should reinforce trust.

9. WhatsApp Community SOP

Welcome Sequence

Upon joining, each founder receives:

1.  Welcome message

2.  Community introduction

3.  Group guidelines

4.  Campaign timeline

5.  Team contacts

6.  Introduction prompt

Community Rules

Members may:

✓  Introduce themselves

✓  Share milestones

✓  Ask for advice

✓  Seek collaborations

✓  Share business updates respectfully

Members may not:

✗  Spam

✗  Harass

✗  Discriminate

✗  Mislead

✗  Recruit aggressively

Weekly Community Rituals

| Monday | Founder Introduction |
| --- | --- |
| Tuesday | Business Tip |
| Wednesday | Collaboration Request |
| Thursday | Founder Story |
| Friday | Win of the Week |
| Saturday | Resource Share |
| Sunday | Reflection & Gratitude |

These rituals encourage consistency and participation.

10. Content Production SOP

Every content piece must pass through:

Idea

↓

Script

↓

Design

↓

Review

↓

Approval

↓

Scheduling

↓

Publishing

↓

Performance Review

Content Checklist

Before publishing:

✓  Founder is accurately represented

✓  Branding is consistent

✓  CTA is clear

✓  Spelling is correct

✓  Visual quality is high

✓  Caption aligns with brand voice

✓  Hashtags are relevant

No asset should be published without final review.

11. Live Session SOP

48 Hours Before

- Confirm founder availability

- Share discussion outline

- Test technical setup

- Prepare promotional assets

24 Hours Before

- Publish reminder

- Share story countdown

- Confirm internet connection

- Reconfirm timing

During Live — Host Responsibilities

- Welcome audience

- Introduce founder

- Guide conversation

- Encourage audience interaction

- Mention campaign purpose

- Close with CTA

After Live — Within 24 Hours

- Share highlights

- Thank founder

- Save recording

- Repurpose clips

- Collect feedback

12. Community Engagement SOP

Community Manager responsibilities:

- Respond daily

- Encourage participation

- Celebrate milestones

- Connect founders

- Resolve conflicts quickly

Healthy engagement matters more than high member count.

13. Paid Ads SOP

Daily review:

- Budget spent

- Cost per application

- Reach

- Click-through rate

- Conversion rate

If performance drops significantly, pause and optimise before increasing spend.

14. Analytics & Reporting SOP

Maintain a live dashboard tracking:

- Founder applications

- Accepted founders

- Active founders

- Followers gained

- Reach

- Engagement

- Saves

- Shares

- Story mentions

- Live attendance

- WhatsApp participation

A daily snapshot should be recorded for trend analysis.

15. Crisis & Escalation SOP

| Level 1 Minor | Examples: - Missed reply - Incorrect graphic - Minor scheduling issue Response: Handled by the relevant team member. |
| --- | --- |

| Level 2 Moderate | Examples: - Founder dissatisfaction - Technical issues during live - Community disputes Response: Escalate to Campaign Lead within 2 hours. |
| --- | --- |

| Level 3 Critical | Examples: - Reputational risk - Legal concerns - Public controversy - Serious code-of-conduct violation Response: Campaign Lead assumes direct control and documents all decisions. |
| --- | --- |

The guiding principle is always to protect founder dignity and preserve community trust.

16. Campaign Closing SOP

Within 72 hours of campaign completion:

✓  Publish gratitude message

✓  Share campaign recap

✓  Announce Spotlight recognition

✓  Send founder appreciation messages

✓  Collect testimonials

✓  Archive campaign assets

✓  Update internal documentation

Every participant should feel acknowledged.

17. Post-Campaign SOP

Within One Week — Internal Retrospective

Discuss:

- What worked?

- What failed?

- What surprised us?

- What should improve?

- What should never change?

Document all learnings for the next edition.

Founder Follow-Up — Within 14 Days

- Send feedback form

- Invite continued participation

- Share upcoming opportunities

- Encourage collaboration within the community

The relationship should continue beyond the campaign.

18. Campaign Health Dashboard

At the end of each week, review:

Growth

Applications

Followers

Reach

Engagement

Comments

Shares

Saves

Story interactions

Community

Active founders

Collaboration requests

Conversations

Retention

Impact

Founder testimonials

New opportunities created

Audience sentiment

Stories amplified

A campaign should never be judged by numbers alone.

19. The Operational Golden Rule

When faced with uncertainty, choose the action that:

- Strengthens trust.

- Protects founder dignity.

- Encourages collaboration.

- Reflects TLT's values.

- Creates long-term impact over short-term attention.

20. Final Declaration & Internal Motto

Naari Led Vyapaar is not successful because it is well-organised. It is successful because every process exists to serve a person.

Behind every application is a dream.

Behind every business is a family.

Behind every story is courage.

Our responsibility is to honour that courage with professionalism, empathy, and excellence.

Every checklist.

Every meeting.

Every post.

Every message.

Every decision.

Should remind us that we are not simply running a campaign.

We are building a movement that helps women entrepreneurs feel seen, supported, and celebrated. And movements are built one meaningful interaction at a time.

Internal Motto

Operational excellence creates trust.

Trust creates community.

Community creates impact.

Impact creates legacy.

Naari Led Vyapaar

Discover. Connect. Rise.

An Initiative by The Legit Talks  |  SOP Manual — Version 1.0  |  Confidential